## In Scope (hidden)
|  | GDU | JGG
Step 1 | Establish a working group for ongoing standardization collaboration with senior executive sponsorship by with nominated members ​from JGG and GDU side for each part of the delivery lifecycle.​ | SME GDU Estimated capacity (%) Nilesh Awaghan IND Lily Gilbero PH 10% Lukasz Filipiak PL 15% Oswaldo Ferreira PT 10%
| Understand Fujitsu Activate 3.0 from Ookubo San | Schedule a meeting ookubo.manabu@fujitsu.com
Establish formal communication with the Japan Activate 3.0 team to obtain the full methodology package ​
Request access to the complete Activate 3.0 methodology developed by Fujitsu Japan.
Access Complete Methodology from Fujitsu Japan​
Request supporting materials such as:​ Templates and accelerators aligned with SAP Activate phases (Discover, Prepare, Explore, Realize, Deploy, Run).
Gap Analysis for DSS and SLM Integration: Compare Fujitsu Japan’s Activate 3.0 with SAP’s standard Activate methodology and identify what’s missing for DSS and SLM Integration.​
Step 2 | Create new documentation templates as required​
Define Fujitsu Activate Methodology Integrated Mandatory Standards (IMS)​
Six Phases - Total 41 Documents to be created
Step 3 | Speak to Perpetual + team
Work with the perpetual team to Finalize the tempalates as per fujitsu standards
Step 4 | Build Knowledge Base & Training​
Create a single (Japan and international) repository linked to the global SAP portal to store methodology documents, accelerators, and templates for projects.​
Conduct training workshops for project managers, consultants, and delivery leads to ensure consistent application.​
Roll out certification tracks internally aligned with SAP Activate professional certification (SAP Certified Associate – SAP Activate Project Manager).​
Step 5 | Pilot Implementation​
Apply the integrated Fujitsu Activate methodology on a small to mid-sized SAP S/4HANA project as a pilot.​
Capture lessons learned, refine templates, and update QMS accordingly.​
Step 6 | Formalize in QMS​
Document and embed the refined methodology into the Fujitsu India QMS for SAP projects.​
Ensure auditable compliance and alignment with global Fujitsu standards.​
Establish a continuous improvement loop where feedback from projects feeds into methodology updates.​
Step 7 | Client-facing Differentiation​
Use this as a competitive differentiator in SAP RFPs and proposals, showing clients that Fujitsu not only follows SAP Activate but also enriches it with decades of Fujitsu project experience and project localization.

## Classification
https://pages.community.sap.com/topics/activate | Nilesh |  | Nuno |  | Lukasz |  | Lily | Document Link from Sap Roadmap\
Discover Phase | Mandatory / Optional | Document Link from Sap Roadmap | Mandatory / Optional | Document Link from Sap Roadmap | Mandatory / Optional | Document Link from Sap Roadmap | Mandatory / Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/phaseaccelerator/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Strategic Planning | Mandatory |  |  |  | Mandatory | No documentation as a single document for this activity. | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DACE33C9ECC12B
Create an Innovation Strategy and a High-Level Road Map | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DACFB4749F412D
Explore SAP Business Technology Platform | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/FA163E6071AE1EDC94BFBB09A51243DA
Make yourself familiar with SAP Extension Suite | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/FA163E6071AE1EDC94BFBE831CDD83F5
Make yourself familiar with SAP Integration Suite | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/FA163E6071AE1EDC94BFC1B9823343FA
Accelerate Your Innovations with the Help of Intelligent Technologies | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501ED79CAFEC3D2F010F95
Create a 360-Degree View on Security | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501ED79CAFEFE9D10CCF98
Define the Analytics Architecture | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DAD2207743812D
Make yourself familiar with Implementation Road Maps of SAP Activate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/9C659B670D40400DB217F6DA58558442
Conversion Readiness Assessment | Mandatory |  |  |  | Mandatory | The Conversion Readiness Assessment is, in practice, a report/summary of the SAP Readiness Check results (dashboard + export/report from the tool), rather than a classic Word/PowerPoint template named precisely ‘Conversion Readiness Assessment’. | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/07A6AFA7228D4064B418D04B0A0EAD8A
Check the Conversion Readiness of SAP ERP | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DAD80B85F6014C
Conduct Functional Review Workshop | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/BF9EE07D8C484AAEADBCF9C14F33FC1E
Conduct Technical Review Workshop | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/255BD174906E4354BE5147123BDF4274
Application Value and Scoping | Mandatory | [6 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DAD4214A78C12F
Discover the Value of SAP S/4HANA for Your Company | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DAD58DAB84412F
Understand how to Design Business Processes following the Clean Core Paradigm | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/D71DBB98485C4A348EC6F284990FB203
Understand how to Achieve Clean Processes and a Clean Process Framework in an SAP S/4HANA New Implementation Project | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/F5DE42CB232C4414A7710BB9F6F0E632
Understand how to Achieve Clean Processes and a Clean Process Framework in an SAP S/4HANA Conversion Project | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/88CFC965B1034606B413660166C52E4E
Run a Usage and Data Profiling Analysis | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/74B79050B9BC4F0AA0D0C21F260D0335
Perform a Business Scenario & Solution Mapping | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DADE2BE405814F
Run the Establish the Business Value of User Experience Workshop | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/53073ACA1FEE4F469C7E17ADB919CE73
Create a Solution Architecture | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/FA163EF018EC1EDCB8BD20CA494ECA53
Define the Implementation Strategy | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DAD9E55E4E814C
Create a Strategic Road Map & Value Case | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DAEA699ECE815A
Trial System Provisioning | Mandatory |  |  |  | Mandatory | https://www.sap.com/documents/2019/04/4276422b-487d-0010-87a3-c30de2ffd8ff.html | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F501EE6B1DB6274DC4E8266
Provide a Trial System | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE/node/901B0E6D3F441ED9A78F12A387E01AA3
Prepare Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Project Team Enablement | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Familiarize with Offerings for SAP Enterprise Support Customers | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Familiarize with SAP Value Assurance Service Offering | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Familiarize with SAP MaxAttention / SAP ActiveAttention Service Offering | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Self-Enable on Tools and Methodology for Project Management: SAP Solution Manager, SAP Cloud ALM, and SAP Activate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Familiarize with the Clean Core Concept | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Self-Enable on SAP Signavio Process Insights and SAP Signavio | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Self-Enable on SAP LeanIX | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Conduct Project Team Enablement on Fit-to-Standard | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Self-Enable on SAP Business Technology Platform | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Self-Enable on SAP Fiori for SAP S/4HANA | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Self-Enable on SAP S/4HANA Migration Cockpit | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Conduct Key User Training | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Prototype | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Run Prototyping | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Transition Planning | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/PP_010.zip https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Familiarize with typical Clean Core Aspects in a Conversion Project to SAP S/4HANA | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Check the Conversion Readiness of SAP ERP | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Decide on Conversion Strategy | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Run a Usage and Data Profiling Analysis | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define Scope and Objectives | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Determine Business Process Performance Baseline | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Model As-Is Business Processes | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define Cutover Approach | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Clarify Custom Code Adaption | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Clarify Usage of SAP Business Technology Platform | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Run the User Experience Strategy and Guiding Principles Workshop | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Run the Scope and Envision the Future Workshops | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define the UX / UI strategy | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Clarify Operational Readiness | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define Technical Architecture | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define the Data Migration Approach and Strategy | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Perform Data Volume Planning | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Clarify the impact on your Authorization Concept | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Prepare Interface Register | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Run a Legacy Impact Analysis on Interface Inventory and Data Integration | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Run a first Assessment on Output Management | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Run a Technical Security Self Check | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Transition Preparation | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Execute on Follow-Ups from Transition Planning | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Perform Customer-Vendor Integration to SAP Business Partners | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Clean up Financial Business Data Inconsistencies | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Check Partner Add-ons | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Archive Data | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Decommission Unused Code | [6 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Improve Custom Code Quality Measures | [6 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Set Up and Configure SAP Business Technology Platform | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define the Objects for Business Data Validation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Prepare Tools for Project Support | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Project Initiation | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/PM_01.doc https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Conduct Handover Meeting(s) from Opportunity Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Review Order Form with Customer | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Identify Stakeholders, Stakeholders’ Requirements and Expectations and Project/Deliverable Acceptance Criteria | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Set Stakeholder Expectations for Agile Project | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Create Project Charter | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Create Project Management Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Request Knowledge Assessment: CQC for Transformation Assessment | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Establish Project Governance | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/Project%20Guideline%20Template.docx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define Roles and Responsibilities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define Project Organization | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Establish Solution Standardization Board | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Review Project Management Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Plan Project | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/PP_010.zip https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Create Scope Statement | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Create WBS | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Create Project Schedule | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Create Budget | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Plan Quality | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Plan Communications | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Plan Risks | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Plan Procurement | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Plan Stakeholders Management | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Project Kick-Off and On-Boarding | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/PM_13.pptx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Prepare for Kick-off Meeting | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Conduct Kick-off Meeting | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Prepare Team On-boarding Document | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
On-board Project Team | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Project Standards, Infrastructure, and Solution | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define Project Standards | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Determine Operational Standards | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Set Up Project Team Logistics and Infrastructure | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Setup and Test Remote Support | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Execution, Monitoring, and Controlling of Results | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Direct and Manage Project Execution | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Monitor and Control Project Activities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Manage Issues, Risks and Changes | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Communicate Status and Progress to Project Stakeholders | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Change Concept | Optional | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/Change%20Concept_v1.0.pptx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define Organizational Change Management Roles | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Staff Organizational Change Management Resources | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Define Organizational Change Management Set-up | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Change Plan | Optional | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/ChangePlan_v1.0.pptx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Determine Action Areas for Organizational Change Management | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Develop First Version of the Change Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Establish Updating Procedure for the Change Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Stakeholder Analysis (RACI, ORG Structure) | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/StakeholderMatrix_v1.0.pptx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Identify Stakeholders | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Assess Stakeholders | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Derive Stakeholder Engagement Activities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Communication Analysis and Plan | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/PM_21.ppt https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Analyze Communication Channels | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Analyze Communication Needs | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Create Communication Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Enablement Strategy | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/S4H_997%20Enablement%20Strategy%20Overview.pptx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Review Enablement Strategy Research and Interviews | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Document Enablement Strategy | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Learning Needs Analysis for Project Team | Optional | [5 empty] | Optional | https://support.sap.com/content/dam/SAAP/SAP_Activate/Learning%20Needs%20Analysis%20Project%20Team%20Overview.pptx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Identify Learning Needs for Project Team | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Create Learning Curriculum based on SAP Standard Learning | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Conduct Business Review | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Content Development Tool Deployment | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Prepare and Install a Content Development Tool | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Phase Closure and Sign-Off Phase Deliverables | Mandatory | https://pr.alm.me.sap.com/launchpad?sap-support-headless=true&sap-ui-language=en-US&sap-ui-theme=sap_horizon# |  |  |  |  | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Conduct Knowledge Management Gate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Conduct Project Quality Gate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Conduct Project Management Review Service | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Obtain Customer Sign-Off for Phase Completion | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Explore Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE
Phase Initiation | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A0991B739FDB8F06
Review Deliverables of Explore Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A0991D7CF2A80F07/901B0E6D3F441ED8A0991B739FDB8F06
Review Acceptance Criteria | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A0991EF46D21EF0A/901B0E6D3F441ED8A0991B739FDB8F06
Review RACI Chart for Explore Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A0991FA75F8C2F0A/901B0E6D3F441ED8A0991B739FDB8F06
Learning Needs Analysis for Users | Optional | [5 empty] | Optional | https://support.sap.com/content/dam/SAAP/SAP_Activate/Learning%20Needs%20Analysis%20Users%20Overview.pptx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/25A92B3A6E7E436F839B4A47E8442018
Identify Learning Needs Identification Process | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/58895CD8E58E4E99B3A3945653EFE8AF/25A92B3A6E7E436F839B4A47E8442018
Create Learning Curriculum | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/63D78B33F9564F22A63ECDBAE8C3DFDF/25A92B3A6E7E436F839B4A47E8442018
Review Enablement Business Review | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/B7CD345479A341C2908643A051891B5E/25A92B3A6E7E436F839B4A47E8442018
Activate Solution | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9530EB4EF3E2CE
Finalize Mandatory System Preparation Activities (System Conversion only) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A0995C7467480FAA
Reconfirmation of Scope for Activation (New Implementation only) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D953257268022CE
Activation of Best Practices and Test-Activated Processes (New Implementation only) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9533E2290F02CE
Set up Integration with other Test Systems | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501EE9A59E34CB9B77D7B2
Fit-to-Standard Workshop Preparation | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF0B0BDB1CE0302
Prepare and Schedule Workshops | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2AC2D02FAC696
Workshop Participant Enablement | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2B407D594869C
Fit-to-Standard System Preparation | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2BB364923C6BC
Prepare sample data | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2BF484BB846BE
Enhance system with additional configuration | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2C24158A926C1
Fit-to-Standard Workshops and Documentation | Optional | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/S4HANA_WRICEF_Functional_Design_Templates.zip https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2C4FECDA906C2
Fit-to-Standard Workshops Execution | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2C974660846C4
Fit-to-Standard Workshop Documentation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2CAE12163E6C7
Fit-to-Standard Workshop Validation | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2CFB65942E6E6
Prioritize Delta Requirements | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2D11EC59106E6
Gap Validation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2D46FCAF9E6E7
Design Workshops and Documentation | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2D72BF5C9C6E9
Design | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2D914E12846E9
Define Business Process Target State | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163E6071AE1EDC95DB756B3003C778
Design Review and Customer Sign Off | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2DB02C090A6E9
Perform design review | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2DD8DDD4386EB
Perform validation and approval | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDAADF2DF06209266EB
UX Activation and Design | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501ED7B2E923CB45429B6E
UX Activation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501ED7B2E92522B4335B6E
UX Design | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501ED7B2E92698F855DB6E
Security Design | Optional | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/S4H_131.doc https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501ED6B3AA94E1110319A2
Define Security Infrastructure | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501ED6B3AA96F8864219A2
Data Volume Design | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D954B185CC9C2CE
Get Transparency on the HANA DVM Quick Wins | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9555E668B5A2CE
Optional: Set Up a DVM Strategy for Business Documents | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9556C3300722CE
Get Transparency on Open Business Documents | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9556D1B91B02CE
Adapt your DVM Strategy | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9557CD53D6E2CE
Data Migration Design | Optional | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/S4H_134.docx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9560FB6F60E2CE
Conduct Data Migration Assessment | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D957353C24402CE
Run a Data Audit in the Source Systems | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D957353C244E2CE
Finalize the Data Migration Approach and Strategy Document | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D95741D31ECA2CE
Define Specifications for Data Migration | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D95757764F322CE
Set up and Configure Data Migration Tools | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D957060ED2BE2CE
Perform Data Cleansing Activities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EEB9784D114F5E0D2C2
Custom Code Impact | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D954F47770322CE
Create a List of Impacted Custom Code Objects | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D955C504DEF42CE
Integration Design | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501EE79CDAC827628C2996
Define Interface Architecture | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501EE79CDACA9FF0438997
Consider Clean Core Aspects for Integration | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/8F18E384738948129136194449B6B37D
Prepare Integration Design | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501EE79CDACBE911C36999
Analytics Design | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501EE79CC6973F6311DF8E
Design Analytics Architecture | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501EE79CC69977D621DF8E
Test Planning | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/S4H_438 Detailed Test Schedule Template.xlsx?logActivity=true https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D95588E7260A2CE
Make yourself Familiar with the Tools in Test Management, and Set Up Test Management | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D955CF9F60342CE
Determine Test Scope | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D955CF9F60422CE
Detailed Test Planning | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D955DC097D2C2CE
Sandbox Setup / Conversion | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D955FB284A022CE
Set Up SANDBOX (System Conversion scenario only) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501EE9A59FC3AFD9905A9E
Downtime Optimization Preparation (System Conversion scenario only) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9571A43278A2CE
Set Up SANDBOX (New Installation scenario only) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D95729804D182CE
DEV Setup / Conversion | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D95617263A462CE
DEV Setup (New Implementation) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9578C2252CE2CE
DEV Setup (System Conversion) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9579E331D4E2CE
DEV Setup (Selective Data Transition) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/B7AB1660372944B69D703FA634DDF5A2
Activate SAP Fiori in DEV | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/FA163EAF25B21EDBB2C342781BC24A4E
Sizing | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D95640E247822CE
Perform / Check initial Sizing | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D957B9A62F402CE
Technical Architecture and Infrastructure Definition | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9564EB96B542CE
Discover Technical Boundary Conditions | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D958285FEA022CE
Create Technical Solution Map | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D958285FEA102CE
Decide on Integration with Cloud Applications | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D958451F0C622CE
Hardware Selection and Utilization | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501ED9A5AB1F63DB144F73
Develop Virtualization Strategy | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F501ED9A5AB29064A548F78
Design Network | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D958614A767A2CE
Test Preparation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D958614A76882CE
Technical Design | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/AGS_58.docx https://support.sap.com/content/dam/SAAP/SAP_Activate/AGS_59.docx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D95671EBB8402CE
Create a Technical Solution Design Document | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9587FE395202CE
Operations Impact Evaluation | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9569DE2CFF22CE
Operations Impact Evaluation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/001999B7BD851ED68D9588C4B8F342CE
Execution / Monitoring / Controlling Results | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441EE8A0A5A0CFF8F88E4C
Update Project Management Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441EE8A0A5A1E26CB2CE4C
Direct and Manage Project Execution | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441EE8A0A5A35F026CAE50
Conduct SCRUM Meetings | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441EE8A0A5A4111FB6EE50
Monitor and Control Project Activities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441EE8A0A5A4C8C7046E50
Manage Issues, Risks and Changes | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441EE8A0A5A57EC380EE50
Communicate Status and Progress to Project Stakeholders | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441EE8A0A5A635B044AE50
Release and Sprint Plan | Mandatory | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A099DC15D4E4D104
Update and Prioritize Backlog | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A099DD7A3C6D1105/901B0E6D3F441ED8A099DC15D4E4D104
Estimate Backlog Items Effort | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A099DE312CA1F105/901B0E6D3F441ED8A099DC15D4E4D104
Conduct Release and Sprint Planning Meeting | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441EE8A0A74E37DEE01257/901B0E6D3F441ED8A099DC15D4E4D104
Validate Release and Sprint Plan Against SoW | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A099DF98795D7108/901B0E6D3F441ED8A099DC15D4E4D104
Communication Plan Execution | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/PM_21.ppt https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/B398D682D4D74B5BBE13966AC0E408D6
Prepare Communication Activities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/030F8D2542724CB4B2C659C1E8BAB9FF
Deliver Communication Activities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/89FFAEAD25CF46DC836F6111C030083B
Update Communication Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/C8BF1D232CA7481387FE1EDD4B31CB6C
Phase Closure and Sign-Off phase Deliverables | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A09A351A236E91E6
Request Knowledge Assessment: CQC for Transformation Assessment | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/384D4AD6B6334FEC9B641A8A4C5294EE
Conduct Knowledge Management Gate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A09A368038F551E7
Conduct Project Quality Gate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A09A37407D7DB1E8
Execute Baseline Retrospective | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A09A380A5E81B1EB
Conduct Project Management Review Service | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A09A38C8E8E171EB
Manage Fulfilled Contracts | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A09A3985817631EB
Obtain Customer Sign-Off for Phase Completion | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCC3E4F2C6C2CE/node/901B0E6D3F441ED8A09A3A4ACA1D71EB
Realize Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE
Phase Initiation | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09A7363A5E6928C
Review Deliverables of Realize Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09A764D059F9290
Review Acceptance Criteria | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09A77DEE07F3290
Review RACI Chart for Realize Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09A7891D7AD7290
Plan Realize Phase | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C0CCB24339688
Plan Sprints and Solution Reviews | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C0F42362E5689
Plan Testing | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C10CE7066768A
Enablement Content Development | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/896B374B279B44D183DA76FA588BE2CD
Create a Content Development Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/65C557CD03BC43BBA952B0484CBB164E
Manage Content Design and Content Development | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/F38226FD99AD486B88E4B733F38C50B5
Sprint Initiation (Iterative) | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C2374851CD6C6
Conduct Sprint Planning Meeting (Iterative) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C2462B60416C6
Execution Plan for Realize Phase | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C3D267E62D6F9
Manage Sprints | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C3E47025B96FC
Manage Unit/String Tests | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C3F0AD33D36FD
Manage Integration Test | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C3FC6D513F6FD
Manage Security Test | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C4085F3EEF6FD
Manage User Acceptance Test | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09C414A3DF036FD
Configuration: Introduction | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95C637D16F82CE
Make yourself familiar with Configuration | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441EEA9C82827E32CB12A3
Configuration: Handover | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95C7A2058D02CE
Run Handover Session | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95E90AB9E002CE
Configuration: Main Configuration | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95C885667F02CE
Perform Main Configuration | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95ECD4BE9442CE
Configuration: Unit Test | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95CA36D4DB42CE
Run Unit Test | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95EECFA20502CE
Configuration: String Test | Mandatory | [5 empty] | Optional | https://support.sap.com/content/dam/SAAP/SAP_Activate/R_150.docx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95CB0C6168C2CE
Run String Test | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F07F7B1002CE
Configuration: Solution Walk-Through | Mandatory | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95CC104861C2CE
Run Solution Walk-Through | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F1810B8722CE
Configuration: Bug Fixing | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95CCBC30B002CE
Resolve Identified Issues | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F3AF127462CE
Configuration: Documentation | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501EE88A819087ADF75AEF
Document Configured Settings | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501EE88A81923E84D01B0F
Product Enhancements | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95CE61ED95E2CE
Adjust Affected Existing Custom Code | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/07F7A3F6C7814CBCAFBF28DA72DB0225
Adjust Custom Code with Re-Design or Re-Platforming | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/FA163E6071AE1EEC94BA2E2DEDA5186F
Develop Extensions following the Clean Core Strategy | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/FA163E6071AE1EDC94BFD86248F48425
Custom Development provided by SAP | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F6C4D5D8A2CE
UX Implementation | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/814728BE0B2F4E9F893BF619FBFE49E9
Enhancement and development of user interface | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F60103D622CE
Sprint Closing | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09F4B8D97371E92
Conduct Sprint Review Meeting | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09F4C878BC3DE92
Signoff Sprint Results | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09F4DF6197AFE95
Conduct Sprint Retrospective | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09F4EA8E74B3E95
Security Implementation | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501ED6B3C396CBB0248B1E
Implement Security | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501ED9A5AC80D649A851EC
Data Volume Management Configuration | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95D06C9806E2CE
Cleanup or Archive Data | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F69EA5F802CE
Configure Data Archiving (Design Time) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F7C077A9C2CE
Test execution of Data Archiving (Runtime) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F89043F102CE
Integration Validation | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95D266CC2E02CE
Identify the IV Scope | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F89043F1E2CE
Initiate the Corresponding IV Support Activities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F972DF2C82CE
Initiate SAP Going-Live Check | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95F972DF2D62CE
Data Migration & Verification | Optional | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/S4H_140.xls https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95DB65992222CE
Data Migration (New Implementation) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95FED72A7A22CE
Perform Load & Verification Runs (System Conversion) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95FED72A7B02CE
Selective Data Transition Scenarios | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501ED6A3E800F2908794AE
Custom Code Quality | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501EE9978786BD3751D4BD
Establish / Adjust Custom Code Quality | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501EE997878CAF8F3794C0
Integration Implementation | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501EE79CDBFB747C474C1B
Implement Integration Design | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501EE79CDBFC2B64D44C1B
Validate Integration Implementation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501EE79CDBFCAC3F61CC1B
Analytics Configuration | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95D4FC85E242CE
Technical Setup of SAP S/4HANA embedded analytics | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/FE0692D3FCAF4258A0B1A49F7603B072
Integration with SAP Analytics Cloud | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/C9F3C307B5D84AD09FC0C8FB8D5526FD
End User Enablement for SAP S/4HANA embedded analytics | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/A2EF937C9706430D8C230DE174962099
Test Preparation | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95D893ABBB62CE
Prepare Tests | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95D893ABBB62CE
Test Execution | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95D87596C482CE
Perform Integration / Regression / User Acceptance Test | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95FD024FD522CE
Test Suite Analytics and Reporting | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501EE9BDCD4461E2ADDBA5
QAS Setup/ Conversion | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95D9D6992202CE
QAS Setup (New Implementation) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95FDE8C08A42CE
QAS Setup (System Conversion) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95FDE8C08BC2CE
QAS Setup - (Selective Data Transition) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/6D80C958FB9143D298BB8FED7BB62985
Sizing & Scalability Verification | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95E0A9D8D522CE
Perform Sizing Verification | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D9609787F47C2CE
Perform Scalability Verification | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D9609A2193482CE
IT Infrastructure Setup | Optional | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95E166684302CE
Set Up IT Infrastructure | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D960A6A1867E2CE
Test IT Infrastructure | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D960A87E3D882CE
Operations Implementation | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95E265A2D342CE
Collect detailed Operations Requirements | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501ED6A3E80B475F14D4B7
Roles and Responsibilities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D960B51DA11E2CE
Support Processes and Procedures | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D960B51ED9AA2CE
Operations Support Tools | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D960C525DC4A2CE
Operations Documentation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D960D15763722CE
Knowledge Transfer | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D960D458C5D42CE
Cutover Preparation & Plan NOTE: Separate document and tasks delivered outside of the Master Activate Phases | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/Sol_Pack/BP_BSCON_S4HANAXV1/BP_BSCON_S4HANAXV1_CutoverPlan_EN_XX.xlsm https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D95DC673AFE62CE
Production System Setup | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D960013365AC2CE
Create Cutover Plan (New Implementation) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D960013365BA2CE
Create Cutover Plan (System Conversion) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/001999B7BD851ED68D9600FAD5C3A2CE
Create Cutover Plan (Selective Data Transition) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F501ED6A3E808CF2E4F54B3
Execution, Monitoring and Controlling Results | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09D224472C8D91C
Direct and Manage Project Execution | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09D2357603D191D
Update Project Management Documents | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09D24B17D9AF91D
Manage Project Issues, Risks, and Changes | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/E20136BB03E54A0E90A46E542E92DC56
Communicate Project Status and Progress | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09D2624FEC1B941
Plan and Execute Agile Sprints | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09D26DECF4D3944
Perform Scrum-Of-Scrums Meeting (Iterative) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09D27974E71B944
Detailed Change Impact Analysis | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/DetailedChangeImpactAnalysis_v1.0.pptx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/C5FB143DF3B240108690EDE02E2DFF77
Prepare Change Impact Workshops | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/EECCB49D09044C75A909C9F163B1EB6F
Conduct Change Impact Assessment | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/38C9EB8C173D48EC990AA67BD4EEE981
Manage Change Impacts | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/9ADB828B0CDC4090844BFD32F7FBFAAC
Enablement Delivery | Mandatory | [5 empty] | Mandatory | https://support.sap.com/content/dam/SAAP/SAP_Activate/Enablement%20Delivery%20Overview.pptx https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/4D16E59797B54FD094D796D04D755A53
Plan Learning Logistics | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/EB2B2FF3B5AC4310A78CBE32AC9FE017
Setup System Landscape and Data | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/3853E86FF8024AD29A25979BA10D0661
Deliver Enablement | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/4EDDCCFC04D147948C0DDD72AA8E0FC7
Phase Closure and Sign-Off Phase Deliverables | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09E779B950C9C88
Request Knowledge Assessment: CQC for Transformation Assessment | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/E548ABD55D314A06A04CFE41E99EE605
Conduct Knowledge Management Gate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09E7CC03A041C8C
Conduct Project Quality Gate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09E7D75A1CC3C8C
Execute Baseline Retrospective | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09E7E2985D3FC8D
Conduct Project Management Review Service | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09E7EDEE9D55C8D
Manage Fulfilled Contracts | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09E7F94BB383C90
Obtain Customer Sign-Off for Phase Completion | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD49DCA7E82CE/node/901B0E6D3F441ED8A09E804A0AE5FC90
Deploy Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE
Phase Initiation | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441ED8A09A612209265255
Allocate Resources and Update Project Schedule | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441ED8A09A61EA5AD59255/901B0E6D3F441ED8A09A612209265255
Perform Kick-off Meeting | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441ED8A09A62B28BC17255/901B0E6D3F441ED8A09A612209265255
Integration Validation | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D972F3D63E482CE
Finalize Integration Validation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D973E1657F762CE
Operations Readiness | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D9736D57966C2CE
Operational Readiness (System Conversion) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D97464B9B9642CE
Operational Readiness (New Implementation) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D97464B9B9722CE
Dress Rehearsal | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D9730AD202AE2CE
Finalize IT Infrastructure Services | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D9744FBE1C742CE
Perform Cut-Over Rehearsal | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D973ED9020D82CE
Execution, Monitoring and Controlling Results | Optional | [5 empty] | Optional | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A48F5F6FE6CB94
Update Project Management Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A491C95C694BBA/901B0E6D3F441EE8A0A48F5F6FE6CB94
Direct and Manage Project Execution | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4933F5996ABBD/901B0E6D3F441EE8A0A48F5F6FE6CB94
Monitor and Control Project Activities | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A493F45698ABBD
Manage Issues, Risks and Changes | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A494A91CEFABBD
Conduct Project Quality Gate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A49564F70C6BBD
Communicate Status and Progress to Project Stakeholders | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A49FE840C78BC4
Release Closing | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4AFD01541CBF7
Prepare Product Backlog for Next Release/Sprint | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4B0ED5F83CBF8
Conduct Release Retrospective | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4B1C258B36BF9
Update the Release and Sprint Plan | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4B28683BD2BF9
Production Cutover | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D97325CC30222CE
Convert Productive System (System Conversion) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D974065E8E3A2CE
Production Cutover (New Implementation) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D974138C46842CE
Production Cutover (Selective Data Transition) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F501ED6A3E81AFEA09F14D8
Hyper Care Support | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D9749B114A0A2CE
Monitor Resource Consumption | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F501ED782E4F598441CDA21
Analyze Workload | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F501ED782E503AB20329A4D
Check System Scalability | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F501ED782E5102B975A5A53
Follow-up on GoingLive Check (Verification Session) | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F501ED782E515EB57345A57
Delete Obsolete Data with the “Obsolete Data Handling Tool” | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F501EE99789222A918DD833
Handover to Support Organization | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D974CF8D5B002CE
Resolve and Close Open Issues | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D974FF7F80662CE
Handover Operations Responsibility | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/001999B7BD851ED68D9750BF5D2B62CE
Project Closure and Sign-Off Project Deliverables | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4EF8024E14C95
Conduct Knowledge Management Gate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4F10422DB4C99
Conduct Project Quality Gate | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4F1BC0CD1EC99
Manage fulfilled Contracts | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4F273D8B32C99
Resolve and close open Issues | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4F33220FAEC99
Finalize Project Closeout Report | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4F3F13237AC99
Obtain Sign-off for Project Closure and Results Acceptance | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmap/S4HANATRANSONPRE:001999B7BD851ED68BCCD7F18BA222CE/node/901B0E6D3F441EE8A0A4F4AF0C17AC99
Run Phase | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Operate Solution | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Safely and Efficiently Operate the new Solution | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Continuously Optimize IT Operations | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Improve and Innovate Solution | Mandatory | [5 empty] | Mandatory | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Assess the Value of the SAP S/4HANA Transformation | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Run the User Experience Business Benefits Workshop | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Periodically Update your SAP System | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE
Initiate a new Innovation Cycle | [7 empty] | https://me.sap.com/roadmapviewer/group/AAE80671-5087-430B-9AA7-8FBE881CF548/roadmapcontentpage/S4HANATRANSONPRE:001999B7BD851ED68BCCBFC6CDCF02CE